## Project
Group 3 - HomeStay Booking ¦ Total Project Tracking
Member :HE171401 Nguyễn Tuấn Anh
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Create Account | Authentication | Customer | Register a customer account with required identity and login information. | Phong | Done |  | 2026-08-20
2 | Login / Logout | Authentication | Customer | Authenticate a user, create a session, protect private screens, and allow the user to log out safely. | Phong | Done |  | 2026-08-20
3 | Edit Profile | Account Management | Customer | View and update personal profile information such as name, phone, address, and avatar. | Phong | Done |  | 2026-08-20
4 | Search Homestay | Homestay Booking | Customer | Search available homestays by keyword, location, price range, guest quantity, dates, amenities, and minimum rating. | Phong | Done |  | 2026-08-20
5 | Detail Homestay | Homestay Booking | Customer | View homestay images, location, price, capacity, amenities, cancellation policy, rating, and published reviews. | Đạt | Done |  | 2026-08-20
6 | Book Homestay | Homestay Booking | Customer | Select check-in/check-out dates and guests, apply a voucher, review nightly pricing, and calculate the booking total. | Phong | Done |  | 2026-08-20
7 | Confirm Booking | Homestay Booking | Customer | Submit a booking order with pending status and wait for online payment or host confirmation. | Phong | Done |  | 2026-08-20
8 | View Order History | Booking Management | Customer | View past and upcoming bookings, open booking details, and request cancellation according to policy. | Đạt | Done |  | 2026-08-20
9 | Post Review | Booking Management | Customer | After checkout, submit a 1-to-5 star rating, written review, and experience photos for an eligible booking only. | Đạt | Done |  | 2026-08-20
10 | Choose Payment Methods | Homestay Booking | Customer | Select online or pay-at-homestay payment, view the payment amount, and complete the pending online payment. | Đạt | Doing |  | 2026-08-20
11 | Manage Homestay | Homestay Management | Home Owner | Create, view, edit, hide, and resubmit homestays with information, images, location, amenities, capacity, price, schedule, and payment methods. | Phong | Done |  | 2026-08-20
12 | Manage Voucher | Homestay Management | Home Owner | Create, view, edit, activate, deactivate, and configure voucher rate, limits, validity period, minimum order, and scope. | Đạt | Done |  | 2026-08-20
13 | View Booking Requests | Booking Management | Home Owner | View and filter incoming booking requests for homestays owned by the current host. | Đạt | Done |  | 2026-08-20
14 | Confirm / Reject Booking | Booking Management | Home Owner | Confirm, reject, or cancel a booking and optionally record a reason for the action. | Tuấn Anh | Done |  | 2026-08-20
15 | View Booking Schedule | Booking Management | Home Owner | View upcoming booking dates and manage daily availability and custom prices. | Tuấn Anh | Done |  | 2026-08-20
16 | View Revenue | Revenue Management | Home Owner | View revenue summaries and revenue charts for 7 days, 1 month, and 1 year. | Tuấn Anh | Doing |  | 2026-08-20
17 | View Booking History | Revenue Management | Home Owner | Review booking history and inspect cancellation performance through a dedicated cancellation statistics chart. | Tuấn Anh | Doing |  | 2026-08-20
18 | Manage Accounts | User Management | Admin | View account statistics, search users, edit account information, and activate or block accounts. | Tuấn Anh | Done |  | 2026-08-20
19 | Manage All Homestays | Homestay Data Management | Admin | View homestay statistics, search listings, edit homestay information, change status, and access related review moderation. | Đạt | Doing |  | 2026-08-20
20 | Dashboard | System Management | Admin | View total customers, owners, homestays, bookings, revenue, active listings, and pending requests. | Hưng | Done |  | 2026-08-20
21 | Manage Blog | System Management | Admin | Create, view, edit, publish, unpublish, and delete blog posts. | Hưng | Done |  | 2026-08-20
22 | Manage Banners | System Management | Admin | Create, view, edit, activate, deactivate, and delete homepage banners. | Hưng | Done |  | 2026-08-20
23 | Send Notification | Notification Management | Admin | Send announcements and operational notifications, view notification history, and notify users about booking, payment, account, or system events. | Hưng | Doing |  | 2026-08-20
24 | Manage Reviews | Review Management | Admin | Search reviews, inspect reports, edit review data where permitted, hide/show inappropriate content, and delete reviews. | Hưng | Doing |  | 2026-08-20
25 | Manage Amenities | Homestay Management | Home Owner | Create, view, edit, and delete amenities that can be assigned to owned homestays. | Hưng | Done |  | 2026-08-20
26 | Manage Stay Change Requests | Homestay Booking | Customer | Create, view, and cancel extension or early-checkout requests for an eligible booking. | Tuấn Anh | Doing |  | 2026-08-20
27 | Manage Favorite Homestays | Booking Management | Customer | Add, view, and remove favorite homestays for personalized discovery. | Tuấn Anh | Done |  | 2026-08-20
28 | Process Stay Change Requests | Homestay Management | Home Owner | View, filter, accept, or reject guest requests to extend a stay or check out early. | Hưng | Done |  | 2026-08-20
29 | Manage Cancellation Policies | Homestay Data Management | Admin | Create, view, edit, activate/deactivate, and delete cancellation policies used by homestays and bookings. | Hưng | Done |  | 2026-08-20

## Iter1
Iteration Tracking - Iteration 1
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Create Account | Authentication | Register a customer account with required identity and login information. | Phong | Done
2 | Login / Logout | Authentication | Authenticate a user, create a session, protect private screens, and allow the user to log out safely. | Phong | Done
3 | Edit Profile | Account Management | View and update personal profile information such as name, phone, address, and avatar. | Phong | Done
4 | Search Homestay | Homestay Booking | Search available homestays by keyword, location, price range, guest quantity, dates, amenities, and minimum rating. | Phong | Done
5 | Detail Homestay | Homestay Booking | View homestay images, location, price, capacity, amenities, cancellation policy, rating, and published reviews. | Đạt | Done
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
6 | Book Homestay | Homestay Booking | Select check-in/check-out dates and guests, apply a voucher, review nightly pricing, and calculate the booking total. | Phong | Done
7 | Confirm Booking | Homestay Booking | Submit a booking order with pending status and wait for online payment or host confirmation. | Phong | Done
8 | View Order History | Booking Management | View past and upcoming bookings, open booking details, and request cancellation according to policy. | Đạt | Done
9 | Post Review | Booking Management | After checkout, submit a 1-to-5 star rating, written review, and experience photos for an eligible booking only. | Đạt | Done
10 | Choose Payment Methods | Homestay Booking | Select online or pay-at-homestay payment, view the payment amount, and complete the pending online payment. | Đạt | Doing
26 | Manage Stay Change Requests | Homestay Booking | Create, view, and cancel extension or early-checkout requests for an eligible booking. | Tuấn Anh | Doing
27 | Manage Favorite Homestays | Booking Management | Add, view, and remove favorite homestays for personalized discovery. | Tuấn Anh | Done
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
11 | Manage Homestay | Homestay Management | Create, view, edit, hide, and resubmit homestays with information, images, location, amenities, capacity, price, schedule, and payment methods. | Phong | Done
12 | Manage Voucher | Homestay Management | Create, view, edit, activate, deactivate, and configure voucher rate, limits, validity period, minimum order, and scope. | Đạt | Done
13 | View Booking Requests | Booking Management | View and filter incoming booking requests for homestays owned by the current host. | Đạt | Done
14 | Confirm / Reject Booking | Booking Management | Confirm, reject, or cancel a booking and optionally record a reason for the action. | Tuấn Anh | Done
15 | View Booking Schedule | Booking Management | View upcoming booking dates and manage daily availability and custom prices. | Tuấn Anh | Done
16 | View Revenue | Revenue Management | View revenue summaries and revenue charts for 7 days, 1 month, and 1 year. | Tuấn Anh | Doing
17 | View Booking History | Revenue Management | Review booking history and inspect cancellation performance through a dedicated cancellation statistics chart. | Tuấn Anh | Doing
25 | Manage Amenities | Homestay Management | Create, view, edit, and delete amenities that can be assigned to owned homestays. | Hưng | Done
28 | Process Stay Change Requests | Homestay Management | View, filter, accept, or reject guest requests to extend a stay or check out early. | Hưng | Done
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
18 | Manage Accounts | User Management | View account statistics, search users, edit account information, and activate or block accounts. | Tuấn Anh | Done
19 | Manage All Homestays | Homestay Data Management | View homestay statistics, search listings, edit homestay information, change status, and access related review moderation. | Đạt | Doing
20 | Dashboard | System Management | View total customers, owners, homestays, bookings, revenue, active listings, and pending requests. | Hưng | Done
21 | Manage Blog | System Management | Create, view, edit, publish, unpublish, and delete blog posts. | Hưng | Done
22 | Manage Banners | System Management | Create, view, edit, activate, deactivate, and delete homepage banners. | Hưng | Done
23 | Send Notification | Notification Management | Send announcements and operational notifications, view notification history, and notify users about booking, payment, account, or system events. | Hưng | Doing
24 | Manage Reviews | Review Management | Search reviews, inspect reports, edit review data where permitted, hide/show inappropriate content, and delete reviews. | Hưng | Doing
29 | Manage Cancellation Policies | Homestay Data Management | Create, view, edit, activate/deactivate, and delete cancellation policies used by homestays and bookings. | Hưng | Done
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document